## Sheet1
Project Deadlines |  | Prototyping Plan
Prototype 1 (Feb. 26) |  | Prototype 1 | Parts | Person Responsible | Deadline | Testing
Pototype 2 (Week of Mar. 20) |  |  | Cardboard Structure | Chulang, Alpesh, Zexuan | 2017-02-26
|  | Prototype 2 |  |  | 2017-03-12
|  |  | Wheels, gears, shafts | Chulang | 2017-03-05
|  |  | Motors | Dan | 2017-03-07
|  |  | Chassis | Zexuan | 2017-03-08
|  |  | Attaching motor to chassis | Chulang | 2017-03-08
|  |  | Battery Compartment | Dan, Chulang, Zexuan | 2017-03-09
|  |  | Remote control | Dan, Alpesh, Faven | 2017-03-10
|  |  | Assembly |  | 2017-03-11 | Test the drive system.
|  | Final Prototype |  |  | 2017-03-19
|  |  | Height adjustment system | Alpesh | 2017-03-15
|  |  | Tray | Faven | 2017-03-15
|  |  | Assembly | Entire Team | 2017-03-16 | Test all aspect of available features
Torque (Nm): | 1.25 | Torque (oz-in): | 177.0149
Mass of cart: (kg) | 5
speed: (m/s) | 0.5