{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":15,"n_cols":4,"rows_kept":15,"cut":false,"hidden":false,"merged":[[1,1,1,3],[3,1,3,3],[9,1,9,3]]}
[]
[null,"Schedule"]
[null,"Task","Start Date","End Date"]
[]
[null,"Deliverable document report (Dhara)","2019-10-20","2019-10-29"]
[null,"Create subtitles (Imaan)","2019-10-20","2019-10-29"]
[null,"Develop initial design for primary screen (Matan)","2019-10-20","2019-10-29"]
[null,"Develop initial design of user's instructions (Omar)","2019-10-20","2019-10-29"]
[null,"Prepare for client meeting (Sean)","2019-10-20","2019-10-29"]
[]
[null,"Refine designs (Dhara)","2019-10-31","2019-11-07"]
[null,"Complete subtitles + Create instructions (Imaan)","2019-10-31","2019-11-07"]
[null,"Refine designs (Matan)","2019-10-31","2019-11-07"]
[null,"Refine designs (Omar)","2019-10-31","2019-11-07"]
[null,"Prepare for client meeting + Work on deliverable report (Sean)","2019-10-31","2019-11-07"]